Progress Update #2

Due Thursday, October 29, 2020

Submit/Post to School Website

School Performance Plan Implementation:  Using data from your fall interim assessment(s) please provide a short narrative to capture your progress in the implementation of your School Performance Plan thus far.

Professional Development

Progress

Progress

- 100% of PLC have been facilitated and conducted with administrator and Data Coach supporting teachers implementation of PLCs. - Instructional coaching and peer observation being conducted for all staff at need-based supports from administrator, data coach, TNTP - Professional development related to virtual and distance learning

Barrier

Barriers

-There have been some barrieers in regard to staff abaility and familiarity with technology and the use of technology in instruction.

Next Steps

Next Steps

- Continued Professional Learning aligned to Tier 1 instruction and PLCs. - Continued Professional Learning with backwards planning, instructional coaching, and Peer Observations - Continued Professional Learning related to distance and virtual learning - Full time ETS in the works to be hired

Family Engagement

Progress

Progress

- 92% of families attended Fall Conferences. Continued follow up is being done to meet with families. - 100% of students (13) on the Path Way to Chronically Absent received Tired Letters for attendance and supports. - CIS personnel making home visits

Barriers

Barriers

- Families availability to attend conferences. - CIT - Hiring timeline - Grant approval

Next Steps

- Training of New Staff

- Coordination of roles and responsibilities of CIS

- Coordination of use of technology to get into contact with parents efffectively

Curriculum, Instruction, Assessment

Progress

Progress

- Collaboration with TNTP center around Curriculum, Instruction, and Assessment support. Identifying areas of need for instructional coaching and curriculum/assessment development. - Conducted Math Benchmark Assessments for grades 3-5. Assessment results used for data-driven instructional decision making. - Consistent and regular instructional coaching provided to all teachers and staff supporting students aligned to the goals 1 & 2 of the SPP.

Barriers

Barriers

- Integrating the curriculum into the new world of virtual and distance learning.

- Next Steps Continued Professional Learning aligned to Tier 1 instruction and PLCs.

- Continued Professional Learning with backwards planning, instructional coaching, and Peer Observations